## Gantt Chart w % Complete
A Hybrid Deep Reinforcement Learning and LLM Framework for Real-Time Distillation Optimization
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7
Building Simulation Model
| Crude Assay Data collection | 2026-03-01 | 1 | 2026-03-06 | 5 | 5 | 0 | Suman S | 100%
| Configuring all data in new sim | 2026-03-01 | 1 | 2026-03-06 | 5 | 5 | 0 | Suman S | 100%
| Adding all streams and equipments | 2026-03-01 | 1 | 2026-03-06 | 5 | 5 | 0 | Suman S | 100%
| Convergence of model | 2026-03-02 | 2 | 2026-03-07 | 5 | 5 | 0 | Suman S | 100%
| Review of column profile | 2026-03-03 | 3 | 2026-03-13 | 10 | 3 | 7 | Suman S | 30%
Training of Deep Reinforcement Learning model
| Setting up venv & lib | 2026-03-03 | 3 | 2026-03-08 | 5 | 3.5 | 1.5 | Suman S | 70%
| Coding of script | 2026-03-03 | 3 | 2026-03-08 | 5 | 0.25 | 4.75 | Suman S | 5%
| Optimization of states and actions | 2026-03-06 | 6 | 2026-03-11 | 5 | 0 | 5 | Suman S | 0%
| RL agent building | 2026-03-06 | 6 | 2026-03-21 | 15 | 0 | 15 | Suman S | 0%
Building of AI Agent
| Setting up workflows | 2026-03-10 | 10 | 2026-03-25 | 15 | 0 | 15 | Suman S | 0%
| Configuration of AI Agent | 2026-03-12 | 12 | 2026-03-27 | 15 | 0 | 15 | Suman S | 0%
| Testing of AI Agent | 2026-03-14 | 14 | 2026-03-29 | 15 | 0 | 15 | Suman S | 0%
| Setting up of vector database | 2026-03-16 | 16 | 2026-03-18 | 2 | 0 | 2 | Suman S | 0%
| Testing of Agentic RAG | 2026-03-16 | 16 | 2026-03-31 | 15 | 0 | 15 | Suman S | 0%
Development of End-User application & Other deliverables
| Interface of product pricing entry | 2026-03-01 | 1 | 2026-04-05 | 35 | 0 | 35 | Suman S | 0%
| Interface for model monitoring | 2026-03-02 | 2 | 2026-04-06 | 35 | 0 | 35 | Suman S | 0%
| Interface for agent interaction | 2026-03-03 | 3 | 2026-04-07 | 35 | 0 | 35 | Suman S | 0%
| Report & Other deliverables | 2026-03-01 | 1 | 2026-04-08 | 38 | 3.8 | 34.2 | Suman S | 10%
Formulas:
END DATE = [START DATE]+5